## Sheet1
Recomendation for standard complexity tasks 0.3, for high complexity 0.35
Feature\story name | Development |  |  |  |  | Testing |  |  | Joint activities |  | Risks | Development Final |  | Testing Final | Total, Md |  | Assumption
|  |  | 0.15 | 0.1 |  | 0.35 | 0.2 |  | 0.04 | 0.03
| FE | BE | Code review | Unit tests | Code refactoring (insert mannualy) | General test | Test documentation | Performance\e2e | Requrements analysis. WBS prepation, grooming | Communication (team communication with BA and each other) | Risks (insert manually if needed) | BE | FE | Tesing |  | Total Hours
Order creation from Jira ticket | 1.5 | 2 | 0.525 | 0.2 | 0 | 1.5 | 0.7 |  | 0.257 | 0.19275 | 0 | 2.5124 | 2.0124 | 2.3499 | 6.8748 | 54.998
Sorting by Quantity | 0.25 |  | 0.0375 | 0 | 0 | 0.25 | 0.05 |  | 0.0235 | 0.017625 | 0 | 0.032458 | 0.28246 | 0.31371 | 0.62862 | 5.029
Administration permission | 1 | 3 | 0.6 | 0.3 | 0 | 1.5 | 0.8 |  | 0.288 | 0.216 | 0 | 3.618 | 1.618 | 2.468 | 7.704 | 61.632
Filtering by Stauts and Requester | 0.5 |  | 0.075 | 0 | 0 |  | 0.1 |  | 0.027 | 0.02025 | 0 | 0.05325 | 0.55325 | 0.11575 | 0.72225 | 5.778
|  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 | 0
Test on different screen res./systems/browsers | [14 empty] | 0 | 0
Demo prepation (for BA or other task stakeholders) | [14 empty] | 0 | 0
Deployment (insert manually if needed) | [10 empty] | Total MD | #REF! | #REF! | #REF! | 15.9296 | 127.437